## Roadmap
Phase | Task | Status | Notes
Phase 1 | Regression baseline gates and governance | Completed | CI regression gates, PR rationale checks, baseline drift artifacts
Phase 2 | Cascaded speed/current FOC with anti-windup | Completed | Speed PI, current PI, saturation and anti-windup
Phase 2 | d-q decoupling feed-forward | Completed | Optional d/q decoupling toggles and telemetry
Phase 2 | Angle observer modes (Measured/PLL/SMO) | Completed | User-selectable observer mode with GUI controls
Phase 2 | Sensorless startup observer handoff | Completed | Initial observer to target observer transition logic
Phase 2 | Inverter non-idealities: device drop/dead-time | Completed | Base non-ideal inverter model
Phase 2 | Inverter non-idealities: current-dependent conduction | Completed | Effective conduction resistance term
Phase 2 | Inverter non-idealities: switching-frequency term | Completed | Current- and frequency-dependent switching loss term
Phase 2 | Observer confidence and adaptive handoff | Completed | Confidence metric + confidence hold-time criterion
Phase 2 | Adaptive handoff criteria enhancements | Completed | Confidence hysteresis + hold-time fallback to startup observer
Phase 2 | Observer confidence metrics refinement | Completed | Confidence component breakdown (EMF/speed/coherence) + EMA/trend diagnostics
Phase 2 | Observer reliability analytics | Completed | Confidence duration counters, threshold crossings, handoff quality/stability KPIs
Phase 2 | Startup transition diagnostics export/reporting | Completed | Diagnostics included in regression drift report artifacts
Phase 2 | Transition KPI threshold gates in CI | Completed | Warn/fail startup transition KPI thresholds enforced in CI with threshold summary artifact
Phase 3 | Sensorless control maturity | Completed | Confidence/speed-weighted sensorless angle blending for low-speed robustness + telemetry
Phase 3 | Power factor correction | Completed | Implemented PFC foundation: metrics + controller + simulation telemetry + GUI controls/monitoring + dedicated PFC analysis plotting (2026-03-13)
Phase 3 | Efficiency optimization | Completed | Implemented efficiency telemetry, loss tracking, efficiency analysis plotting, and heuristic tuning recommendations (2026-03-13)
Phase 4 | Hardware integration | In Progress | Hardware I/O abstraction layer added to SimulationEngine with mock DAQ backend, runtime enable/disable, diagnostics, and tests (2026-03-15).
Phase 3 | Inverter realism enhancement (switchable multi-physics blocks) | Completed | Implemented configurable inverter realism: device/dead-time/conduction/switching/diode/min-pulse/bus-ripple/thermal/phase-asymmetry with telemetry, plotting, export, and tests (2026-03-15).
Phase 4 | Hardware integration GUI wiring (mock backend controls) | Completed | Added GUI controls for enabling mock DAQ backend, noise/seed configuration, engine wiring, export metadata, and regression tests (2026-03-15).
Phase 4 | Hardware monitoring telemetry in GUI | Completed | Added live monitoring indicators for hardware enabled/connected/backend/write-read counters/I-O error flag in monitoring tab with regression coverage (2026-03-15).
Phase 4 | Communication terminology clarification in GUI | Completed | Renamed user-facing hardware monitoring/control wording to communication terminology to avoid confusion with inverter hardware modeling (2026-03-15).
Phase 4 | Standard startup sequence (FOC+V/f): align, open-loop ramp, closed-loop handoff | Completed | Implemented full startup phase machines for FOC and V/f. Sensored FOC skips open-loop phase and goes align->closed-loop. Added GUI controls, monitoring telemetry, export metadata, and regression tests. | 2026-03-15
Phase 3 | FOC auto-tuning no-timeout stabilization at 1000 RPM | Completed | Adjusted convergence gating: orthogonality check is now load-aware at low Iq, preserving strict gate under meaningful torque; validated accepted/full_converged at 1000 RPM with overcurrent abort policy (2026-03-17). | 2026-03-17
Phase 4 | GUI-triggered loaded calibration workflow | Planned | Expose loaded-point calibration directly in the accessible GUI so users can launch it without leaving the application (2026-03-17).
Phase 4 | Single-active-job enforcement for simulation/calibration | Planned | Block new long-running launches while an older simulation or calibration process is still alive; require explicit completion or cancellation first (2026-03-17).
Phase 4 | Process lifecycle tracking and guaranteed shutdown | Planned | Track every spawned process and ensure it is closed when finished or cancelled, avoiding orphaned workers (2026-03-17).
Phase 4 | Bottom status bar for simulation and process telemetry | Planned | Add accessible status reporting for active process state, estimated remaining simulation time, and other runtime indicators (2026-03-17).
Phase 4 | PWM-period CPU load estimator | Planned | Estimate CPU load from control-computation time divided by PWM period budget, matching embedded controller timing analysis (2026-03-17).
Phase 5 | Microcontroller-faithful simulation scheduling | Planned | Reproduce real MCU sequencing for sampling, control calculation, and command application timing in the simulator (2026-03-17).
Phase 5 | Shunt and differential-amplifier phase-current measurement model | Planned | Model shunt-based current sensing with amplifier gain, offset, and backward-capacitance-derived cutoff frequency for more realistic hardware behavior (2026-03-17).
Phase 5 | Current-measurement error sensitivity and harmonic impact study | Planned | Quantify the effect of current-measurement gain and offset errors on control behavior and phase-current harmonics (2026-03-17).
Phase 3 | Voltage-headroom-based field weakening scheduler | Completed | Reworked FW to regulate dq voltage headroom with tunable target voltage reserve, including GUI wiring and telemetry for injected Id/headroom (2026-03-17).
Phase 5 | Topology-aware inverter current-sense GUI and integration validation | Completed | Added 68 Phase D GUI/integration tests covering lifecycle, calibration completion paths, monitoring updates, FFT window wiring, and current-sense behavior for single/double/triple shunts; main_window.py coverage reached 84% (2026-03-19). | 2026-03-19